## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-20 |  |  |  |  | mayo | [13 empty] | junio | [27 empty] | julio
Scrolling Increment: | 1 | time axis 2022-05-21 to 2022-07-15
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-05-21 to 2022-07-15
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-20 | 3 | 2022-05-21: 2; 2022-05-22: 2
Task 2 | Milestone |  |  | 2022-05-25 | 1 | bar: 2022-05-25
Task 3 | Low Risk |  | 50% | 2022-05-17 | 10
Task 4 | Milestone |  |  | 2022-06-09 | 1 | bar: 2022-06-09
Task 5 | Med Risk |  | 10% | 2022-05-26 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-05-26 | 13
Task 2 | On Track |  | 50% | 2022-05-28 | 9
Task 3 | Low Risk |  | 33% | 2022-06-02 | 11
Task 4 | Milestone |  |  | 2022-06-04 | 1 | bar: 2022-06-04
Task 5 |  |  |  | 2022-06-05 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-04 | 4
Task 2 | Med Risk |  |  | 2022-06-07 | 14
Task 3 | On Track |  |  | 2022-06-22 | 6
Task 4 | Goal |  |  | 2022-06-26 | 3 | 2022-06-26: 2; 2022-06-27: 2; 2022-06-28: 2
Task 5 | Low Risk |  |  | 2022-05-26 | 19
TITLE 4
Task 1 |  |  |  | 2022-06-29 | 15
Task 2 |  |  |  | 2022-07-13 | 5
Task 3 | Milestone |  |  | 2022-08-24 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Informe Trabajo Profesional
Project Start Date: | 2022-04-20 |  |  |  |  | abril | [13 empty] | mayo | [27 empty] | junio
Scrolling Increment: | 0 | time axis 2022-04-20 to 2022-06-14
Milestone description | Category | Assigned to | Progress | Start | Days | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m
Nombre del proyecto
Definir nombre del proyecto | Low Risk | Name | 0 | 2022-04-20 | 4
Introducción y objetivos
Redactar la introducción | Med Risk |  | 0 | 2022-04-23 | 8
Definir objetivos generales y especificos | Med Risk |  | 0 | 2022-04-20 | 4
Marco Teorico
Crear un repositorio de posbiles fuentes | Med Risk |  |  | 2022-05-01 | 3
Filtrar Fuentes | Med Risk |  |  | 2022-05-04 | 4
Leer fuentes | Med Risk |  |  | 2022-05-04 | 4
Seleccionar fragmentos que pueda usar | Med Risk |  |  | 2022-05-04 | 4
Redactar marco teórico | Med Risk |  |  | 2022-05-08 | 28
Indice Desglosado
Construir índice | Low Risk |  |  | 2022-06-14 | 1
Antecedentes del tema
Redactar antecedentes del tema | Med Risk |  |  | 2022-05-08 | 7
Definicion del problema o contexto de la participacion
Redarcar la definición del problema o contexto de la participación | High Risk |  |  | 2022-04-24 | 7
Análisis y metodología empleada
Investigar Metodologías | High Risk |  |  | 2022-05-15 | 2
Redactar la metodología empleada | High Risk |  |  | 2022-05-18 | 4
Participación profesional
Redactar la participacion profesional | High Risk |  |  | 2022-05-22 | 14
Resultados obtenidos
Validar los objetivos/requerimientos | High Risk |  |  | 2022-06-05 | 7
Conclusiones
Redactar las conclusiones | High Risk |  |  | 2022-06-05 | 7
Bibliografía
Seleccionar Tipo cita | Low Risk |  |  | 2022-05-08 | 2
Automatizar tipo cita excel | Low Risk |  |  | 2022-05-08 | 2
Revisar bibliografia final | Med Risk |  |  | 2022-06-12 | 2
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-20 |  |  |  |  | mayo | [6 empty] | junio | [34 empty] | julio
Scrolling Increment: | 5 | time axis 2022-05-25 to 2022-07-19
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-05-25 to 2022-07-19
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-20 | 3
Task 2 | Milestone |  |  | 2022-05-25 | 1 | bar: 2022-05-25
Task 3 | Low Risk |  | 50% | 2022-05-17 | 10
Task 4 | Milestone |  |  | 2022-06-09 | 1 | bar: 2022-06-09
Task 5 | Med Risk |  | 10% | 2022-05-26 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-05-26 | 13
Task 2 | On Track |  | 50% | 2022-05-28 | 9
Task 3 | Low Risk |  | 33% | 2022-06-02 | 11
Task 4 | Milestone |  |  | 2022-06-04 | 1 | bar: 2022-06-04
Task 5 |  |  |  | 2022-06-05 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-04 | 4
Task 2 | Med Risk |  |  | 2022-06-07 | 14
Task 3 | On Track |  |  | 2022-06-22 | 6
Task 4 | Goal |  |  | 2022-06-26 | 3 | 2022-06-26: 2; 2022-06-27: 2; 2022-06-28: 2
Task 5 | Low Risk |  |  | 2022-05-26 | 19
TITLE 4
Task 1 |  |  |  | 2022-06-29 | 15
Task 2 |  |  |  | 2022-07-13 | 5
Task 3 | Milestone |  |  | 2022-08-24 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one